SESSION 5

Standing it up — ninety days, three workstreams

A mandate with owners and a stop-doing list. Not a transformation program.

How to use this script

- Bring the charter, the SLA page, the dictionary draft, and the purchase freeze. This session binds them into one mandate.

- Output: sponsor, reporting line, max three workstreams, 90-day calendar, stop-doing list, and a decision on who does the work — existing person, hire, or fractional. Not a 40-item roadmap.

- If Sessions 1–4 left holes, fill only what blocks the ninety days. Do not reopen bake-offs.

In the room: the people who must sign the charter. If they are not here, you can draft. You cannot mandate.

| Block | Time |
| --- | --- |
| Recap and contract | 5 min |
| Prerequisites — pass/fail | 8 min |
| The 90-day shape | 12 min |
| Who does the work | 10 min |
| Workshop: mandate | 20–25 min |
| Close | 3 min |

0. Recap and contract — 5 min

SAY

The pillars were diagnosis. Today is commitment. I will not add a fourth workstream. I will not turn this into a year-long transformation. We will write a ninety-day mandate the sponsor can repeat in one breath: who is accountable, which three things move, what we will stop.

WRITE AND LEAVE UP

- Ninety days. Three workstreams. A stop-doing list.

- If it is not on the charter, it is not in the quarter.

1. Prerequisites — pass or fail — 8 min

SAY

Do not start the clock if these are missing. A mandate without them is theater.

| Must exist | If missing |
| --- | --- |
| Named sponsor | You have a study group, not a system. |
| Reporting line for the referee | Go back to Session 1. Do not staff a vacuum. |
| Charter signed or dated this week | Schedule a 30-minute close-out. Do not launch. |
| One shared revenue goal | Not fourteen KPIs. One sentence all three functions ladder to. |

SAY

A seam SLA and a draft dictionary are the first work, not a fourth prerequisite. If they are already done, the ninety days get easier. If they are not, they are workstreams one and two.

2. The ninety-day shape — 12 min

SAY

This is a sequence, not a slogan. Steal it. Do not decorate it.

DAYS 1–30 — DIAGNOSE

- Path map from first touch to renewal — only enough to find leaks.

- Data-quality snapshot against the draft dictionary.

- Stack inventory and the freeze already written.

- Top five leaks. Baseline the few numbers you will live with.

DAYS 31–60 — STABILIZE

- Freeze the dictionary. Finance signs.

- Run the one handoff SLA.

- Weekly pipeline inspection inside the system of record — not a spreadsheet sidecar.

- One executive dashboard. One number per KPI.

DAYS 61–90 — INSTITUTIONALIZE

- Cadence: weekly inspection, monthly handoff review, quarterly stack and capacity.

- Change control for definitions.

- One strategic output the sponsor can use: coverage, capacity, or forecast reliability.

- Decide keep / kill / hire at day 90 — not at day 5.

SAY

Foundation, then a working seam, then a rhythm. Companies skip to dashboards and call it month ninety on day twelve.

3. Who does the work — 10 min

SAY

This is not automatically a new department. Match the shape of the company to the hat, not the other way around.

| Situation | Honest option |
| --- | --- |
| Early, messy, one motion | One senior generalist or fractional lead plus the charter. Specialists later. |
| Scaling, several leaks | Head of RevOps plus one or two specialists already in the building. |
| Complex, multi-product | Central referee with embedded ops. Still one dictionary. |

SAY

Do not open a requisition to avoid naming the person who already sits closest to the work. Do not dump the hat on a CRM admin and call it strategy. Budget talk today is only: people versus cleanup versus tools — and tools are frozen unless they fix a named gap.

4. Workshop — write the mandate — 20–25 min

SAY

Five decisions. We write them on the charter or on a one-page mandate that attaches to it. If a decision will not land, we write the blocker. We do not invent a sixth workstream to hide it.

| Decision | Write this |
| --- | --- |
| 1. Sponsor | Name. Public owner of the charter. |
| 2. Reporting line | Referee reports to CRO / CEO / COO. |
| 3. Three workstreams | Default: dictionary, one seam, one source of truth / freeze. Kill a default only if that work is already done. |
| 4. Who does the work | Named human, even if interim or fractional. Hours they can give. |
| 5. Stop-doing | Two or three habits that die: extra dashboards, vanity MQL targets, forecast-in-spreadsheet, tool buys without review. |

SAY

Put day 30, 60, and 90 on the sponsor’s calendar before you leave. A mandate without those three meetings is a memo.

5. Close — 3 min

SAY

You now have a quarter, not a philosophy. Next session is how you will manage it after it exists: the short scorecard, the cadence, the failure modes. That meeting is shorter. The work is already scoped.

LEAVE BEHIND

- Signed or dated-this-week charter

- Mandate page: five decisions

- Calendar holds for day 30 / 60 / 90

- Date for Session 6

If the room derails

| They say | You say |
| --- | --- |
| Let’s run a six-month transformation. | Six months is how this becomes a program office. Ninety days, then we decide. |
| We need a full roadmap first. | The roadmap is the three workstreams. Detail lives inside them, not on a fourth slide. |
| Can we add enablement / website / pricing? | Not in this quarter. If everything is RevOps, nothing is. |
| We’ll start when we hire. | Then the first workstream has no owner. Name an interim or do not start the clock. |
| Keep the old dashboards during transition. | One legal dashboard. The rest are the stop-doing list. Parallel truth is how day 90 looks like day 0. |

What you will not do in Session 5

- Open a PMO.

- Approve four workstreams.

- Wait for a perfect hire to begin diagnose.

- Leave without dates on the sponsor calendar.

Success test

The session worked if the sponsor can say, without notes: who the referee reports to, which three things move this quarter, and which two habits are dead. Day 30 is on the calendar.